## Slide 1: The Behavioral Health Information Notices

## Slide 2: BHIN 23-068 vs. BHIN 24-045 & Revised Implementation Plan
Compare BHIN 23-068 and BHIN 24-045
Explain how the policy change affects providers
Provide an updated implementation roadmap for ASAM 4th Edition tools

## Slide 3: Overview of BHIN 23-068
Released by DHCS under Cal-AIM
Required use of: ASAM Criteria® Assessment Interview Guide, OR ASAM CONTINUUM
Effective date: January 1, 2025

## Slide 4: Overview of BHIN 24-045
Issued December 23, 2024
Postpones the implementation of assessment tools from BHIN 23-068
Triggered by release of ASAM Criteria 4th Edition
Updates to tools are currently in progress

## Slide 5: Policy Comparison Table
Topic | BHIN 23-068 | BHIN 24-045
ASAM Assessment Tool Requirement | Mandates use of ASAM Criteria® Assessment Interview Guide or ASAM CONTINUUM software starting Jan 1, 2025. | Postpones this requirement until further notice.
Tool Version | Based on ASAM Criteria 3rd Edition. | Recognizes release of ASAM Criteria 4th Edition; updates underway.
Alternative Tools | Only ASAM Guide, CONTINUUM, or validated DHCS-approved tools permitted. | Providers may continue to use current tools already in use.
Implementation Date | January 1, 2025 for ASAM tool use. | Future date TBD by DHCS once 4th Edition tools are ready.
Other Policies in BHIN 23-068 | All other documentation and assessment guidance remain. | Still remain in effect and are not changed by BHIN 24-045.

## Slide 6: Revised Implementation Plan - Phase 1(Q1)
Continue using current ASAM-based tools
Inform staff of postponement
Delay ASAM 4th Edition training plans
Monitor for DHCS updates

## Slide 7: Revised Implementation Plan - Phase 2 (Q2)
Review ASAM 4th Edition changes
Select tool: Guide, CONTINUUM, or validated tool
Plan and schedule staff training
Start updating internal policies and forms

## Slide 8: Revised Implementation Plan - Phase 3 (Q3-Q4)
Organization-wide rollout of selected tool
Provide support to staff during transition
Monitor assessment quality
Maintain compliance and readiness for audit

## Slide 9: Key Take Aways
BHIN 24-045 provides flexibility and time
ASAM 4th Edition tools are coming
Use this delay to plan effectively
Stay aligned with BHIN 23-068 requirements